## Complaint Letter
LHC OUTSTANDING AUDIT FINDINGS
STATUS REPORT-CONFIDENTIAL
HUD's Subject: Complaint Regarding the Louisiana Housing Corporation's Administration of the HOME Investment Partnerships (HOME) Program
[5 empty] | Date Report Received: | 2017-02-21
[5 empty] | Date Response Sent: | 2017-03-03
[5 empty] | Update: | 2017-05-15
Finding Number | Responsible Department | HUD's Finding | HUD's Corrective Action Plan/Response | LHC Corrective Action Plan Response | Finding Status (Open-Closed) | LHC's Next Step
RM15001 | HOME | Failure to Conduct Subrecipient Monitoring, Site inspections, and Client Eligibility | The LHC must make a monitoring schedule of all Tenant Based Rental Assistance (“TBRA”) subrecipients for client eligibility and unit inspections; and conduct monitoring visits of each and submit the monitoring reports along with a certification regarding client eligibility to this Office. | The current administration is focused on providing affordable housing to the State, as well as addressing any issues either within LHC or with recipients of LHC funds. As such, the LHC intends to use every legal remedy at our disposal to resolve this issue. LHC intends to hold the responsible parties accountable. We would ask that you allow the leadership of LHC the opportunity to quickly resolve any potential repayments, while establishing and providing to you a step by step action plan. It should be noted that the LHC has incorporated additional policies and controls. | Open | PENDING CLOSURE: In the response dated March 3, 2017, the LHC attached a copy of the construction monitoring manual as well as TBRA monitoring reports. We anticipate that this will satisfy HUD's concerns.
RM15002 | HOME | Files Lacking Documentation Showing PJ's Initial, Progress, and Final Inspections (Louisiana Family Recovery Corps-LFRC) | LHC should include in their processes a method for monitoring construction work during the different phases of construction. Please provide this Office with documentation that initial, progress and final inspections were performed during the construction of the project. | The current administration is focused on providing affordable housing to the State, as well as addressing any issues either within LHC or with recipients of LHC funds. As such, the LHC intends to use every legal remedy at our disposal to resolve this issue. LHC intends to hold the responsible parties accountable. We would ask that you allow the leadership of LHC the opportunity to quickly resolve any potential repayments, while establishing and providing to you a step by step action plan. It should be noted that the LHC has incorporated additional policies and controls. | Open | ACTION: This matter has been forwarded to outside counsel for their review and recommendations. In addtition, a letter was drafted for the inspector that the HOME Department feels may have done the final inspections for this program.
RM15003 | HOME | Files Lacking Documentation Showing Property Eligibility (Louisiana Family Recovery Corps-LFRC) | LHC must monitor the files of each participant and provide this Office with documentation showing that all participants in the program are eligible and property eligibility via a certification listing the client names and an eligibility status. | The current administration is focused on providing affordable housing to the State, as well as addressing any issues either within LHC or with recipients of LHC funds. As such, the LHC intends to use every legal remedy at our disposal to resolve this issue. LHC intends to hold the responsible parties accountable. We would ask that you allow the leadership of LHC the opportunity to quickly resolve any potential repayments, while establishing and providing to you a step by step action plan. It should be noted that the LHC has incorporated additional policies and controls. | Open | ACTION: This matter has been forwarded to outside counsel for their review and recommendations. In addtition, a letter was drafted for the inspector that the HOME Department feels may have done the final inspections for this program.
RM15004 | HOME | Failure to Recapture Advanced HOME funding in the Amount of $468.492.94 (Natalbany Gardens) | The LHC must repay the $468,492.94 that was disbursed to Natalbany. | The deadline for completion is March 2018 and LHC is working closely with the HUD Field Office and the developer to see this project to completion. We are using this response to further our meeting the deadline goals. We would like the opportunity to move forward with the project. Should it fail, we will follow appropriate and swift recapture protocol. | Open | Once the OIG concerns have been satisfied, LHC will follow HUD's guidance which we anticipate will give us permission to complete the Natalbany Gardens project. If the project is not completed, LHC will follow appropriate and swift recapture protocol.
RM15005 | HOME | Failure to Recapture HOME funding in the Amount of $2,000,000 (Oakmont) | The LHC must immediately repay the $2,000,000 that was disbursed to Oakmont (Live Oaks) in hopes of providing 212 affordable housing units. | LHC has confirmed that HOME funds were used to create HOME assisted units. However, the LHC was made aware that other actions took place outside of our control that limited the availability of those affordable units. The Agency is continuing its review of this matter to determine the appropriate legal remedy. We would ask that you allow the LHC to quickly resolve any repayments with a detailed action plan. | Open | ACTION: This matter has been forwarded to outside counsel for review (Long Law Firm). Once they determine LHC's best and most suitable course of action, we will proceed with resolving this issue by filing suit or entering into some an agreement with the current owners.
RM15006 | HOME | Failure to Execute a Legally-binding Written Agreement before Setting-up Projects in IDIS (Armour Place) | The LHC must develop written policies and procedures to ensure ongoing compliance with this HOME requirement. Also, the LHC must submit the written policies and procedures to this office for review. When the LHC is monitored on-site in the future, HUD staff will reference these policies and procedure when evaluating program files and the overall management of HOME funds. | It should be noted that the Agreement was signed by Inner-City on April 16, 2012 and by the LHC on April 20, 2012. LHC realizes that setting up this activity on April 18, 2012 prior to its final execution is a violation. To ensure that activities in the future are done in accordance with the law, a new policy was implemented and adopted in 2013. Please see the attached policy. | Open | PENDING CLOSURE: An updated policy was submitted to HUD in the March 3, 2017 response that the LHC anticipates will satisfy this finding.
RM15007 | HOME | Failure to Monitor Armour Place Timely (Armour Place) | The LHC must develop policies and procedures that include a project schedule allowing them to be in compliance with the HOME requirement, i.e., monitoring after project construction completion. | The project was completed in IDIS on July 30, 2013. As stated above, the Armour Place final inspection was performed on April 22, 2013 (construction was completed but lease-up had not begun). The regulation cited by the HUD monitor was published July 24, 2013, with an effective date of August 23, 2013. The Armour Place development was subject to the terms set forth in the Final Rule published September 16, 1996. It is our interpretation that the project is in compliance with the governing rule. The project is continuously monitored for long-term compliance monitoring in accordance with program rules and regulations. | Open | PENDING CLOSURE: LHC anticipates that the information provided in their response will satisfy this finding.
RM15008 | HOME | Non-compliant Repayment Agreement (Zydeco Place) | The LHC must return the amount of the disbursed funding to the Treasury Account with nonfederal funds. | We are working closely with the HUD Field Office to properly account for these funds in the IDIS. | Open | LHC is waiting on guidance from HUD to determine the proper manner in which close out these projects.
RM15009 | HOME | Failure to Recapture $168,138.33 in HOME funding (Louisiana Village) | The LHC must immediately repay the $168,138.33 that was disbursed to Louisiana Village. | We are working closely with the HUD Field Office to properly account for these funds in the IDIS. | Open | LHC is waiting on guidance from HUD to determine the proper manner in which close out these projects.
RM15010 | HOME | Failure to Monitor the Construction Progress of the project (Louisiana Village) | The LHC must immediately repay the $168,138.33 that was disbursed to Louisiana Village. | We are working closely with the HUD Field Office to properly account for these funds in the IDIS. | Open | LHC is waiting on guidance from HUD to determine the proper manner in which close out these projects.
RM15011 | HOME | Failure to Maintain Project Records Demonstrating the Source and Applicant of Funds (Louisiana Village) | The LHC must repay the $168,138.33 that was disbursed to Louisiana Village and develop policies and procedures to monitor the progression of all projects. | We are working closely with the HUD Field Office to properly account for these funds in the IDIS. | Open | LHC is waiting on guidance from HUD to determine the proper manner in which close out these projects.
RM15012 | HOME | Failure to Protect the HOME Investment (Louisiana Village) | The LHC must repay the $168,138.33 that was disbursed to Louisiana Village and develop policies and procedures for record keeping. | We are working closely with the HUD Field Office to properly account for these funds in the IDIS. | Open | LHC is waiting on guidance from HUD to determine the proper manner in which close out these projects.
RM15013 | HOME | Non-Compliant Repayment Agreement (One Legacy Place) | The LHC must cease the repayment process that involves drawing funds from one IDIS number and payment for cost of another. Also, LHC must revise its repayment agreement for compliance and submit a copy of it to this office. | We are working closely with the HUD Field Office to properly account for these funds in the IDIS. | Open | LHC will revise its repayment agreement as it relates to Louisiana Village and submit it to the HUD Field Office once guidance is received.
RM15014 | HOME | Questioned Cost (Alsace Lorraine) | The LHC must develop policies and procedures that included the identification of all cost and the training of all staff persons who is responsible for processing payments pertaining to projects payroll and eligible costs. | It should be noted that the above referenced finding listed as 2008-2013 and the finding regarding insurance is from a “Draft” audit for Rapides Station Community Ministries (RSCM). The LHC has reviewed the final Fiscal Year Ending FYE December 31, 2008 report submitted for RSCM; this finding was not included in the final report. The LHC has procedures in place, as a part of the annual sub-recipient monitoring, to ensure HOME funds are used in compliance with the HOME requirements. This includes a review of the entities annual audited financial statements. The LHC has reviewed the referenced LHC Field Report dated July 21, 2008. Issues noted in the report have been substantiated and those validated have been addressed through the following: •Updated program policies and procedures •Providing technical assistance and training to HOME Sub-Recipients •Ongoing HOME training of LHC staff utilizing HUD provided resources, webinars, and onsite training. The final Field Report, dated February 11, 2009, reports the Alsace Loraine project at 99% complete. The LHC has verified the completion and sale of the 20 single family homes per the terms set forth in the grant agreement. | Open | LHC has incorporated into the policy and procedure manual the identification and approval of eligible costs. As soon as the HOME Program staff finalizes the updated policy and procedures manual and obtains management approval, it will be provided to HUD.
RM15015 | HOME | Failure to Effectively Monitor the Financial Position and Project Delays. (Postal Square Townhomes) | The LHC must develop policies and procedures that include compliance monitoring at different intervals during construction that is consistent with payments. | Please be advised that Construction monitoring was performed nine (9) times during the eighteen (18) month construction period. The LHC policy and procedures for construction monitoring is attached. | Open | PENDING CLOSURE: HUD has been provided copies of 9 monitoring reports in regards to Postal Square as well as a copy of the construction monitoring policies and procedures. LHC is waiting on HUD's response. The LHC Legal Department received a subpoena on March 31, 2017 and was answered and remitted on April 4, 2017.
RM15016 | HOME | LHC provided HOME funds to an organization that did not meet the qualifications for CHDO. | The LHC needs adequate systems in place to promote compliance and performance from initial CHDO qualification to, re-qualification, project completion, and monitoring through the affordability period. The LHC must submit a copy of their policies and procedures that constitute the foundation of the program’s operation. | It should be noted that the regulations in place when the development was awarded did not require development experience for an organization to be designated as a CHDO. Therefore, the Inner-City in general and Ms. Dashiel in particular gained the required experience prior to the recertification in 2015. As for GNLCDC, it was awarded the Postal Square project in 2010 and completed the project on October 24, 2012 a period of 18 months. The Postal Square project produced 8 affordable rental housing units through the renovation of a former post office. The project was constructed on budget and within the time allowed by Federal regulations. The person responsible for overseeing the Postal Square project is the same person now serving as the executive director. This experience gained between 2010-2012 meets the requirements now in place to be designated as a CHDO as there is no requirement that more than one person have the capacity to undertake the development of affordable housing. | Open | PENDING CLOSURE: An explanation was provided to HUD which the Corporation thinks will satisfy their concerns. LHC will take additional action if warranted once a response if received from HUD.
RM15017 | HOME | CHDO Certification/Recertification incorrectly | The LHC must develop policies and procedures regarding CHDO certification/recertification that adheres to 24 CFR 92.2. | See Response at 15-016 | Open | PENDING CLOSURE: An explanation was provided to HUD which the Corporation thinks will satisfy their concerns. LHC will take additional action if warranted once a response if received from HUD.

## FY 2008 2009 and 2013
LHC OUTSTANDING AUDIT FINDINGS
STATUS REPORT-CONFIDENTIAL
HUD's Subject: FY 2008, 2009 and 2013 Outstanding Monitoring Findings HOME Investment Partnerships Program (HOME)
[5 empty] | Date Report Received: | 2017-03-06
[5 empty] | Date Response Sent: | 2017-03-31
[5 empty] | Update: | 2017-05-15
Finding Number | Responsible Department | HUD's Finding | HUD's Corrective Action Plan/Follow-up | LHC Corrective Action Plan Response | Finding Status (Open-Closed) | LHC's Next Step
M80003 | Single Family/Owner Rehab | Household Income Not Re-verified | Please certify that applicants whose files are more than six months are re-certified. If LHC has written procedures in terms of income re-certification, please supply. | The LHC HOME Department has written policies and procedures in place in terms of income certification set forth in the HOME Program (Exhibit A-HOME Program Manual Chapter 3:Genral Requirements). The Income Verification section of this Chapter specifically states that, "once initial income verification is completed, a recipient is not required to re-examine the applicant's income unless 6 months has elapsed before assistance is provided." Additionally, the LHC has provided a certification from the current LHC HOME Manager stating that this is the current policy and is being implemented (Exhibit B-Certification of Income Re-Examination). | Open | PENDING CLOSURE: A response was sent to HUD on March 31, 2017. Internal Audit anticipates that the documentation submitted to HUD will satisfy their request.
M80004 | HOME | After-Rehab Appraisal Not Performed | LHFA will provide a signed certification based on Estimate of Value for Owner-Rehab Projects before August 30, 2008. The office has not received the certification. Please provide the certification. | Chapter 4 of the Building HOME training manual, a manual HUD uses for HOME trainings, explains that when using HOME funds, the value of the HOME assisted property after rehabilitation must not exceed 95 percent of the median purchase price for the area, as published by HUD, or, in accordance with the Final Rule, as determined locally through market analysis. The LHC used the Tax Assessment method to determine the value of the replacement housing of the *actual homes rehabilitated in the parish in which the houses were located. None of the property values exceeded the 203(b) limits of each of the homes assisted. The LHC has provided a certification from the current LHC HOME Manager attesting to the facts stated above (Exhibit C-Certification Estimate of Value). Construction for all rehabilitated properties listed in Exhibit C was completed prior to August 30, 2008. Exhibit C-Certification Assessment of Value | Open | PENDING CLOSURE: A response was sent to HUD on March 31, 2017. Internal Audit anticipates that the documentation submitted to HUD will satisfy their request.
M80005 | Single Family | Property Not Listed as Single Family Home/No Title Included | LHFA must revise its application documents to include the proper property type. We also must be assured that a title search will be conducted in the future. Certify that title search was completed for B. Gracie. | The LHC HOME Department certifies it has acquired a title search for Bernice Gracie and that the property is a single family home as evidenced in the title search. (Exhibit D-Certification B. Gracie/Property Type). Additionally, the certification goes on to explain that the LHC does not currently have any HOME homeowner rehabilitation programs underway therefore does not have any applications to submit in response to the audit finding. The certification states that in any future HOME homeowner rehabilitation program applications will contain a check box to indicate the property type. Exhibit D-Certification B. Gracie/Property Type | Open | PENDING CLOSURE: A response was sent to HUD on March 31, 2017. Internal Audit anticipates that the documentation submitted to HUD will satisfy their request.
M80008 | HOME | Funding PHA's without a Contract | LHFA must repay the HOME funds in the a mount of $287,609.93. Please utilize HOME FACTS - Vol. 1 No. 1 for additional information regarding the repayment of HOME funds that have been expended for ineligible activities and/or costs. | The LHC is continuing its review of this matter and gathering off-site documents to resolve the finding. The Corporation would ask that HUD allow for additional time to complete this process. | Open | ACTION: The Internal Audit staff examined the boxes retrieved from Iron Mountain and was unable to locate these files. The HOME Administrator has additional staff searching for these documents. Due to the age of these documents, outside parties (local PHAs) that we contacted have either destroyed these documents or were destroyed by the August floods. LHC will attempt to discuss this matter with HUD.
M80009 | HOME | CHDO Certification Incorrectly | LHC must certify that they have properly certified The Assist in particular in addressing capacity and experience. | The Louisiana Housing Corporation understands HUD had concerns regarding the Assist Agency (Assist), a Community Housing Development the Organization (CDHO), particularly relating to capacity and experience. After re-examining the records the LHC is of the opinion that the Assist Agency was properly certified as a CHDO and currently is a certified CHDO. Under the 1996 HOME Rules (Old Rules) (1996-August 2013), capacity was a requirement only if development funds were granted to the CHDO. In this case, the CHDO received both operating expenses and develop funds therefore capacity and experience was required. The CHDO gained this capacity and experience by partnering with for-profit developers on Low Income Housing Tax Credit projects which provided Assist capacity and experience as a developer. This partnering also provided development training to both the Assist Agency staff and their Housing Director, Ms. Debra Harmon. In August 2013, the New Final HOME Rules took effect (New Rules) (August 2013-present). Capacity is currently a requirement to become a CHDO. The requirement of capacity has been met with the development experience of Ms. Debra Harmon who currently serves as Assist’s Housing Director (Exhibit E-Capacity Experience Debra Harmon-In Globo). From the documents submitted in their CHDO re-certification application, Ms. Harmon assumed this role in 2012 and LHC has certified that she has gained the necessary development experience. Prior to 2012, she served as their Program Director where she had several housing related responsibilities in that position as well. List of Projects for each was provided. | Open | PENDING CLOSURE: A response was sent to HUD on March 31, 2017. Internal Audit anticipates that the documentation submitted to HUD will satisfy their request.
M80010 | HOME | Providing Operating Expenses to unqualified CHDO's | Please clarify that the other agencies (SURC, NOAH and Rebuild Iberia) did not receive funding from LHC and provide the proper documentation for Assist Agency. | The LHC is continuing its review of this matter and gathering off-site documents to resolve the finding. The Corporation would ask that HUD allow for additional time to complete this process. | Open | PENDING CLOSURE: A response was sent to HUD on May 8, 2017. Internal Audit anticipates that the documentation submitted to HUD will satisfy their request.
M13001 | HOME | Executed Written Agreement | LHC must develop a written procedure to ensure that this error does not happen again. That procedure must be submitted to HUD for review. Response is acceptable, please submit a copy of the Policy and Procedures that have been developed. | The LHC is submitting a copy of the Policy and Procedure that required that a fully executed copy of the written agreement be presented to the HOME Program Administrator prior to the project being set up in IDIS. (Exhibit G-Policy and Procedure-Obligations of Funds in IDIS). Exhibit G-Policy and Procedure-Obligations of Funds in IDIS | Open | PENDING CLOSURE: A response was sent to HUD on March 31, 2017. Internal Audit anticipates that the documentation submitted to HUD will satisfy their request.

## OS Findings 3-6-2017 HOME-ESG
LHC OUTSTANDING AUDIT FINDINGS
STATUS REPORT-CONFIDENTIAL
HUD's Subject: FY 2016 Monitoring Visit - Emergency Solutions Grant (ESG) - HOME Investment Partnerships Program (HOME)
[5 empty] | Date Report Received: | 2017-03-06
[5 empty] | Date Response Due: | 2017-04-06
[5 empty] | Update: | 2017-05-15
Finding Number | Responsible Department | HUD's Finding/Condition | HUD's Corrective Action Plan/Follow-up | LHC Corrective Action Plan Response | Finding Status (Open-Closed) | LHC's Next Step
M16001 | HOME | Participant Eligibility Not in File | LHC must submit the documentation that the homebuyers for the three homes constructed were eligible. Income must be supported by source documentation. Indicate if the family's annual income is less than or equal to 80% of the area median income. | LHC has drafted a response to the finding and was submitted to HUD on Wednesday April 6, 2017. The current homebuyer agreement with exhibits was submitted to HUD as requested. | Open | PENDING CLOSURE: LHC mailed a Response to HUD on 4/6/2017. LHC anticipates that the documentation submitted to HUD will satisfy their request.
M16002 | HOME (CHDO) | Executed Written Agreement | During the Exit Conference this issue was discussed and LHC understood that it had to do a better job at tracking agreement dates. LHC is aware of the policies in regards to set-up in IDIS but somewhow missed this particular agreement date. This is a repeat finding. LHC has developed procedures to prevent noncompliance. During our review, we sampled another written agreement with another CHDO to see if LHC was in compliance. The project was the Sugarhouse Phase III project. The written agreement was signed on June 26, 2015 and setup in IDIS on July 1, 2015. Therefore, the LHC is in compliance with this agreement. LHC must assure this Office that the system in place now is improved to ensure compliance. Please submit and updated procedure to this Office. | LHC has drafted a response to the finding and was submitted to HUD on Wednesday April 6, 2017. The current policy and procedure regarding the obligation of funds in IDIS was attached. | Open | PENDING CLOSURE: LHC mailed a Response to HUD on 4/6/2017. LHC anticipates that the documentation submitted to HUD will satisfy their request.

## 2002 Open Findings 3-8-2017
LHC OUTSTANDING AUDIT FINDINGS
STATUS REPORT-CONFIDENTIAL
HUD's Subject: 2002 Open Findings
[5 empty] | Date Report Received: | 2017-03-08
[5 empty] | Date Responsen Due: | 2017-04-08
[5 empty] | Update: | 2017-05-15
Finding Number | Responsible Department | HUD's Finding/Condition | HUD's Corrective Action Plan/Follow-up | LHC Corrective Action Plan Response | Finding Status (Open-Closed) | LHC's Next Step
M2002 | HOME | LHC choose to use the Section 8 definition of income in determining the income eligibility of homebuyers to receive HOME funds under the State's Homebuyer Assistance Program. Incomes of applicants reviewed were not done according to Section 8 requirements. | LHC must ensure that all information regarding income and assets is properly reflected on the application and income computed on these amounts is done in accordance with the requirements of the HOME Program. LHC must take all necessary steps to arrive at an applicant's current income for eligibility purposes. Please provide this office with a written policy regarding LHC's procedures for obtaining and determining an applicant's income under the HOME Program. Please provide the written policy. | LHC submitted the response to the finding to HUD on Monday April 10, 2017 and attached the current policy and procedures regarding the calculation of income. | Open | PENDING CLOSURE: LHC mailed a Response to HUD on 4/10/2017. LHC anticipates that the documentation submitted to HUD will satisfy their request.
M2003 |  | A review of the case files for the above-mentioned applicants revealed that homebuyer agreements are not being executed by LHC. LHC has failed to execute homebuyer agreements with homebuyers who receive HOME funds for interest buy downs and grants for closing costs. Section 92.504 (c)(5)(i) of the HOME Final Rule states that when a PJ provides assistance to a homeowner, a written agreement must conform to the requirements in Section 92.254(a) which includes the value of the property, principal residence requirements, and the resale provisions. | LHC must develop a homebuyer agreement that includes all of the requirements. The agreement must specify the amount of HOME funds, the form of assistance, e.g. grant, amortizing loan, deferred payment loan, the use of the funds i.e. downpayment, closing costs, rehabilitation, and the time by which the housing must be acquired. The agreement must be put into effect immediately. Please supply a current sample homebuyer agreement that meets the issues. | LHC submitted the response to the finding to HUD on Monday April 10, 2017. An excerpt of the homebuyer agreement currently in use and meets the issues stated by HUD was attached with the response. | Open | PENDING CLOSURE: LHC mailed a Response to HUD on 4/10/2017. LHC anticipates that the documentation submitted to HUD will satisfy their request.

## 2011 Monitoring Visit
LHC OUTSTANDING AUDIT FINDINGS
STATUS REPORT-CONFIDENTIAL
HUD's Subject: 2011 Monitoring Visit
[5 empty] | Date Report Received: | 2017-03-08
[5 empty] | Date Response Due: | 2017-04-08
[5 empty] | Update: | 2017-05-15
Finding Number | Responsible Department | HUD's Finding/Condition | HUD's Corrective Action Plan/Follow-up | LHC Corrective Action Plan Response | Finding Status (Open-Closed) | LHC's Next Step
M11002 | HOME | The conflict of interest requirement is not in the written agreement between LHC and LaFleur. Also, the affordabilty period for the project outlined in the agreement is correct. | LHC must provide documentation that the affordability period for the LaFleur project is 20 years instead of the one year specified in the written agreement. Also, a conflict of interest clause must be added to this agreement. | LHC submitted the response to the finding and will submit to HUD by Friday April 8th, 2017. LHC submitted a copy of the written agreement with LaFleur which included an affordablity period of twenty years as well as a conflict of interest statement. | Open | PENDING CLOSURE: LHC mailed a Response to HUD on 4/8/2017. LHC anticipates that the documentation submitted to HUD will satisfy their request.