## Table 1
Project Number | Project Name | Construction Type | Parish | City | Units | TDC | LIHTC Award | Comments
2016-016 | Richland Apartments | Scattered Site/New Construction | Richland | Rayville | 60 | 6822896 | 550000 | Executed credit swap agreement. 6-7-18. Is set to close in November 2018 - 10-31-18
2017-042 | Serenity Village Apartments | Acquisition Rehab | Washington | Franklinton | 32 | 3855410 | 245375 | Carryover documents have been submitted We have not closed. We are working with USDA and Syndicator. We will keep you posted closing. 1-26-18 10% Carryover met 9-20-18.
2017-046 | Lancelot Square Apartments | Acquisition Rehab | St. Charles | Luling | 72 | 5775827 | 306302 | Carryover documents have been submitted We have not closed. We are working with USDA and Syndicator. We will keep you posted closing. 1-26-18. 10% Carryover met 9-20-18.
2017-059 | SBP St. Peter | New Construction | Orleans | New Orleans | 50 | 8487202 | 481137 | Scheduled to close on November 27th. Working on completing HUD 58 clearance. 10-29-18
2017-031 | Uneeda Biscuit | Historic Rehab | Caddo | Shreveport | 32 | 6235124 | 262254 | Carryover documents have been submitted. Met the 10% expenditure requirement 8-28-18
2017-054 | Residences at Tallow Tree | New Construction | Jefferson | Harvey | 78 | 10849033 | 650713 | Plan to close in November or December 2018 - 9-23-18
2017-045 | Pine Cliff Apartments | Acquisition Rehab | St. Tammany | Mandeville | 32 | 3464408 | 177748 | Carryover documents have been submitted We have not closed. We are working with USDA and Syndicator. We will keep you posted closing. 1-26-1810% Carryover met 9-18-18.
2017-020 | The Fairways | Scattered Site/New Construction | Lincoln | Grambling | 40 | 6856100 | 750000 | Carryover documents have been submitted This development has not closed, they are awaiting credit exchange. 10-31-18
2017-115BF | Progress Park | Acquisition Rehab | East Baton Rouge | Baton Rouge | 48 | 5537226 | 180666 | Project Funded in the 2017 CDBG Disaster NOFA and is progressing toward closing
2017-117BF | Cypress at Gardere Affordable | New Construction | East Baton Rouge | Baton Rouge | 99 | 18565353 | 714897 | Project Funded in the 2017 CDBG Disaster NOFA and is progressing toward closing
2017-118BF | Cypress Pointe RAD | Rehab | Washington | Bogalusa | 112 | 14868818 | 529582 | Project Funded in the 2017 CDBG Disaster NOFA and is progressing toward closing
2017-119BF | Hammond Eastside | Historic Rehab | Tangipahoa | Hammond | 28 | 4904059 | 74051 | Project Funded in the 2017 CDBG Disaster NOFA and is progressing toward closing
2017-120BF | Sherwood Oaks | Acquisition Rehab | East Baton Rouge | Baton Rouge | 248 | 27689328 | 1047622 | Project Funded in the 2017 CDBG Disaster NOFA and is progressing toward closing
2017-121BF | Valencia Park of Spanish Town | New Construction | East Baton Rouge | Baton Rouge | 122 | 21006594 | 640635 | Project Funded in the 2017 CDBG Disaster NOFA and is progressing toward closing
2017-122BF | Ardenwood Mixed-Income MF Apartments | New Construction | East Baton Rouge | Baton Rouge | 168 | 26420079 | 528383 | Project Funded in the 2017 CDBG Disaster NOFA and is progressing toward closing
2017-034 | St. John Plaza | New Construction | Ouachita | Monroe | 50 | 8308141 | 557937 | Carryover documents have been submitted The project is waiting on environmental clearance. Return/Reallocation processed on 10/30/18.
2017-022 | Winn Dixie Phase I | New Construction | Orleans | New Orleans | 76 | 19821640 | 750000 | Carryover documents have been submitted. The project has not closed and is on scheduled Received Reprocessing application 3/21/18. VCR Agreement processed on 4/12/18. Received Reprocessing Application 10/17/18
2017-036 | Sunlight Manor II | Acquisition Rehab | Calcasieu | Lake Charles | 38 | 4660011 | 376363 | Carryover documents have been submitted Currently working with HUD on the assignment of the HAP, the TPA (Transfer of Physical Assets) and the approval of the payoff of the existing debt. Architectural plans are being finalized as well. It will be April/May/June before a closing can be scheduled. 1/22/18 Currently proceeding towards a September close. We are awaiting HUD approval of the Transfer of physical assets and assignment of the HAP contract 5/29/18 Return/Reallocation processed on 10/30/18.
2017-040 | Millennium Studios Apartments Phase II | New Construction | Caddo | Shreveport | 68 | 9576464 | 750000 | Carryover documents have been submitted Millennium Studios I & II is located in the City of Shreveport's Choice Neighborhood Implantation are awaiting notification of an award from HUD in mid-to-late June. We anticipate finalizing our financing strategy shortly after receiving notification from HUD. 5-21-18 Request for status update sent to developer 6/27/18. Return/Reallocation processed on 10/30/18.
2017-039 | Millennium Studios Apartments Phase I | New Construction | Caddo | Shreveport | 68 | 9576464 | 750000 | Carryover documents have been submitted Millennium Studios I & II is located in the City of Shreveport's Choice Neighborhood Implantation award from HUD in mid-to-late June. After discussing with our lenders and investors, the consensus was to determine what the final designs and cost would be for the projects should they be awarded Choice funding. We anticipate finalizing our financing strategy shortly after receiving notification from HUD. 5-21-18 Request for status update sent to developer 6/27/18. Return/Reallocation processed on 10/30/18.
2017-035 | Sunlight Manor I | Acquisition Rehab | Calcasieu | Lake Charles | 92 | 10846151 | 750000 | Carryover documents have been submitted Currently working with HUD on the assignment of the HAP, the TPA (Transfer of Physical Assets) and the approval of the payoff of the existing debt. Architectural plans are being finalized as well. It will be April/May/June before a closing can be scheduled. 1/22/18 Currently proceeding towards a September close. We are awaiting HUD approval of the Transfer of physical assets and assignment of the HAP contract 5/29/18 Return/Reallocation processed on 10/30/18.
2017-025 | St Ann Square | Historic Rehab | Orleans | New Orleans | 59 | 10400004 | 750000 | St. Ann Square is progressing. Project submitted a request for reprocessing 4/2018.
2017-053 | Magnolia Crossing RAD | Scattered Site/Acquisition Rehab | Rapides | Alexandria | 49 | 5994591 | 536123 | Carryover documents have been submitted The project has not closed. It was awarded tax credit from the waitlist and is moving towards a Closing .There has been a slight delay with the amount of time HUD has requested to review the project.
|  |  |  | 23 | 1721 | 250520922.38 | 12359788